## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As an IVR developer I want to document existing IVR VXML flows so that I understand legacy call handling | Must Have | Access to existing IVR VXML files | Backend Team | Completed
Sprint 1 | Sprint 1 | US002 | As a backend developer I want to build middleware APIs so that VXML IVR communicates with conversational AI | Must Have | Documented IVR call flows | Backend Team | Completed
Sprint 2 | Sprint 2 | US003 | As a backend developer I want to enable IRCTC booking and enquiry APIs so that users interact through IVR | Should Have | Middleware APIs ready | Backend Team | Completed
Sprint 3 | Sprint 3 | US004 | As a passenger I want to book train tickets through conversational IVR so that booking becomes faster | Must Have | IRCTC booking API access | AI Team | Completed
Sprint 3 | Sprint 3 | US005 | As a passenger I want to check PNR status using voice commands so that I quickly receive journey updates | Must Have | PNR enquiry API access | AI Team | Completed
Sprint 4 | Sprint 4 | US006 | As a tester I want to validate conversational IVR flows so that the system works without errors | Must Have | Conversational flows implemented | Backend Team | In Progress
Sprint 4 | Sprint 4 | US007 | As a DevOps engineer I want to deploy the modernized IVR framework so that users access the upgraded system | Could Have | Backend & AI modules integrated | Both Teams | In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Document existing IRCTC IVR VXML flows | 02-02-2026 | 2026-02-06 | Backend1 | Documentation | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Analyze IVR call handling logic | 2026-02-07 | 2026-02-15 | Backend2 | Analysis | Done | 10 | bar: Day 2 to Day 4
US003 | T3 | Develop middleware APIs for IVR integration | 2026-02-16 | 2026-03-01 | Backend3 | Development | Done | 8 | bar: Day 3 to Day 5
US004 | T4 | Enable booking and enquiry APIs | 2026-03-02 | 2026-03-06 | Backend1 | Development | Done | 12 | bar: Day 4 to Day 7
US005 | T5 | Integrate conversational booking flow | 2026-03-09 | 2026-03-15 | Backend2 | Integration | Done | 10 | bar: Day 5 to Day 8
US006 | T6 | Test PNR status voice query flow | 2026-03-16 | 29-03-2026 | Backend3 | Testing | Done | 8 | bar: Day 6 to Day 8
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Difficulty understanding legacy VXML call flow | Reviewed documentation and clarified architecture
Sprint 2 | Day 6 | API connectivity issue with simulator | Reconfigured middleware endpoints
Sprint 2 | Day 4 | Delay in API response during testing | Optimized API request handling
Sprint 3 | Day 5 | Speech recognition accuracy issue | Updated NLU training data
Sprint 4 | Day 7 | Minor UI alignment issue in simulator | Adjusted UI components

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 02-02-2026 | 15-02-2026 | Backend Team | Improve IVR requirement documentation | Delay in understanding legacy flows | Team collaboration during analysis | Prepare detailed architecture document
2 | 2 | 16-02-2026 | 01-03-2026 | Backend Team | Enhance API development practices | Slow API response during early testing | Regular stand-up discussions | Implement API performance monitoring
3 | 3 | 02-03-2026 | 15-03-2026 | AI Team | Improve conversational flow design | Speech recognition accuracy issues | Continuous testing of AI flows | Improve NLU training dataset
4 | 4 | 16-03-2026 | 29-03-2026 | Backend Team | Strengthen deployment planning | Minor integration bugs in simulator | Good collaboration between AI and backend teams | Create automated deployment checklist