## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Chaithanya | 2026-02-05 | PNR not displayed after booking | Sprint 1 | Backend Team | Functional | Fix API response | 2026-02-06 | Closed | UI-backend mismatch
2 | Chaithanya | 2026-02-06 | Repeated origin prompt issue | Sprint 2 | NLP Team | Functional | State handling fixed | 2026-02-07 | Closed | Flow corrected
3 | Chaithanya | 2026-02-08 | Cancel flow not working | Sprint 2 | Backend Team | Functional | Session fix applied | 2026-02-09 | Closed | PNR not stored
4 | Chaithanya | 2026-02-09 | Invalid train selection crash | Sprint 2 | Backend Team | Validation | Input validation added | 2026-02-10 | Closed | Handled exception
5 | Chaithanya | 2026-02-10 | Speech works but UI not updated | Sprint 3 | Frontend Team | UI | Frontend render fix | 2026-02-11 | Closed | Display issue
6 | Chaithanya | 2026-02-12 | PNR validation incorrect | Sprint 3 | Backend Team | Validation | Validator updated | 2026-02-13 | Closed | Length check added
7 | Chaithanya | 2026-02-14 | Train list static issue | Sprint 3 | Backend Team | Functional | Dynamic filtering pending | 2026-02-15 | Closed | Using static JSON
8 | Chaithanya | 2026-02-16 | Session reset issue | Sprint 3 | Backend Team | Functional | Session persistence fix | 2026-02-17 | Closed | Random reset
9 | Chaithanya | 2026-02-18 | Date input unclear | Sprint 4 | Frontend Team | UI | Improved prompt | 2026-02-19 | Closed | Better UX
10 | Chaithanya | 2026-02-20 | Cancel API not updating DB | Sprint 4 | Backend Team | Functional | DB update fix | 2026-02-21 | Closed | Cancel logic issue

## Sheet2
Logical
User Interface
Maintainability
Standards
Others